## Sheet1
Next review date: 13th March 2023 |  | Green = on track, amber = requires monitoring, red = requires focused attention.
WDES metric | Action | Responsible lead/leads | Progress
1. Percentage of Disabled staff in each of the Agenda for Change Bands 1-9, and VSM, compared to the percentage of staff in the overall workforce (focused actions) | 1.1 Recruit a dedicated Inclusive Recruitment Advisor, who will conduct an end-to-end review of the recruitment process, including revising job description templates and the Trust's Recruitment and Selection Policy. | Adele D'Silva (Head of Workforce Supply) | Nia Thomas in post as of 1st August 2022.
| 1.2 Establish targets and timeline for moving from Disability Confident Employer (Level 2) to Disability Confident Leader (Level 3), based on end-to-end review of recruitment and selection processes and revision of policy in detailed in 1.1 and 2.1. | Nia Thomas (Inclusive Recruitment Advisor) | Revised Recruitment and Selection Policy due end of December 2022. Disability Confident Leader validation template work to start in January 2023. Expected completion by February/March 2023.
| 1.3 Revise the Trust's image library to enhance visible diversity and build meaningful role-modelling into all internal and external communications. | Dan Charlton (Chief Communications Officer) | Staff photos taken in May/June 2022. Image library rolled out in November 2022 with launch of new public website. The library will be kept under review based on both workforce and public feedback.
| 1.4 Analyse data around apprenticeship uptake from Disabled applicants/colleagues, and review apprenticeships offer to encourage applications accordingly. | Stacey Killon (Workforce Transformation Manager for Apprenticeships), Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead), Nia Thomas (Inclusive Recruitment Advisor) | Snapshot data review has been completed for staff from ethnic minority groups, and needs to be replicated for Disabled colleagues. No update at December 2022 review.
| 1.5 Launch a new comms campaign focused on the SPFT Health Passport, and improving disability declaration rates, especially among senior and medical/consultant colleagues. | Dan Charlton (Chief Communications Officer), Chris Picknett (Workforce Equality, Diversity and Inclusion Project Manager) | Campaign is now dependent on launch of WDES Innovation Fund video in January 2023, and accompanying roadshow January 2023-March 2023.
| 1.6 Deliver WDES Innovation Fund work programme of bespoke video and roadshow designed to improve declaration rates, following successful bid for Declaration Rates Award. | Chris Picknett (Workforce Equality, Diversity and Inclusion Project Manager), Dan Charlton (Chief Communications Officer) | Programme launched in November 2022 after slight funding delay. Video and roadshow launch delayed to January 2023. Final report due in April 2023.
2. Relative likelihood of non-disabled staff compared to Disabled staff being appointed from shortlisting across all posts | 2.1 Revise the Trust's standard job advert wording, job description templates and Recruitment and Selection Policy to encourage a diverse range of applicants, and remove potential barriers for applicants from marginalised groups. | Nia Thomas (Inclusive Recruitment Advisor) | Updated advert wording and job description templates to be uploaded onto new dedicated intranet page by end of December 2022, with further revisions likely after start of Scope programme in January 2023. Initial policy rewrite on track for January 2023, with a second version including new manager training/materials expected in April/May 2023.
| 2.2 Create supporting job packs and accessible interview processes for lived experience roles, e.g. peer support roles, in line with the Trust's 2022/23 breakthrough objective of employing more staff with lived experience. | Adele D'Silva (Head of Workforce Supply), Deb Owen (Peer Support Lead), Nia Thomas (Inclusive Recruitment Advisor) | The packs and processes will be designed to give applicants confidence in using their lived experience in their applications, and clarity on how their lived experience will be used in the roles. Nia is working on candidate-facing documents with Deb, and identifying further actions from the Peer Support Strategy, with an update due at the March 2023 review.
| 2.3 Include Experts by Experience (EbEs) on interview and stakeholder panels, to increase focus on values-based interview techniques. | Elaine Colomberg (Interim Director of People Participation), Alex Garner (People Participation Lead), Nia Thomas (Inclusive Recruitment Advisor) | EbE panel representation is in place across the Trust, with Elaine and Alex working on materials for recruiting managers to standardise experience. Nia has included diversification of panels - not just the inclusion of EbEs - in new draft Recruitment and Selection Policy. Update due at March 2023 review.
| 2.4 Adopt Trust-wide values-based interview techniques as part of manager training, including a set of equality, diversity and inclusion (EDI) questions for panels to use. | Nia Thomas (Inclusive Recruitment Advisor) | EDI questions for Board and for bands 2-8a uploaded to intranet in September 2022. Training pilot initially due in January 2023 but delayed slightly as remit has expanded to include more of the recruitment process. Pilot now due March 2023.
| 2.5 Expand appointment options beyond structured interviews, to include work experience, work trials and supported employment. | Nia Thomas (Inclusive Recruitment Advisor), Claire Webster (Interim Chief People Officer) | Details to be included in revised Recruitment and Selection Policy, with initial draft due January 2023. Adele and Nia have met to explore additional options, e.g. guaranteed interview scheme. Project SEARCH confirmed in September 2022, with first cohort due September 2023.
| 2.6 Roll out disability awareness training via Scope's Get Inclusive programme. To be overseen by Project Manager post created through job carving, with the rollout supported by the Education and Training team. Package includes inclusive recruitment workshops for HR Advisors and recruiting managers, toolkits/resources, and the use of Scope's Job Board. | Nia Thomas (Inclusive Recruitment Advisor), Fleur Goff-Beardsley (Workforce Equality, Diversity and Inclusion Project Manager), Claire Marr (Associate Director of OD and Talent Management) | Fleur has arranged contract with Scope, with agreed start date of 9th January 2023.
3. Relative likelihood of Disabled staff compared to non-disabled staff entering the formal capability process, as measured by entry into the formal capability procedure (focused actions) | 3.1 Provide mediation training to service representatives. | Claire Marr (Associate Director of OD and Talent Management), Matt Green (Head of Employee Relations and HR Business Partnering) | Cohorts 1, 2 and 3 delivered in September, October and November 2022, but no further cohorts planned due to business continuity. Claire is working with Adam to explore restorative justice training, and Integrated Care Board (ICB) training is also in early planning stages. Update due at March 2023 review.
| 3.2 Provide equality, diversity and inclusion (EDI), unconscious bias training and Scope training detailed in 2.6 to Employee Relations team. | Claire Marr (Associate Director of OD and Talent Management), Matt Green (Head of Employee Relations and HR Business Partnering), Claire Webster (Interim Chief People Officer) | Matt to discuss EDI and unconscious bias training with HRBPs following December 2022 review, and Claire and Matt to discuss in-house delivery - considering business continuity - to HRBPs, managers and investigating officers. Update due at March 2023 review. Scope training on track, with programme starting in January 2023.
| 3.3 Capture data on issues that were resolved with informal processes. | Matt Green (Head of Employee Relations and HR Business Partnering), Claire Webster (Interim Chief People Officer) | A bespoke database cannot currently be funded, but an interim measure - using a centralised tracker that also captures informal data - is due by end of January 2023, with the caveat that this is a short term solution.
| 3.4 Develop a guide for staff entering the formal capability process, including an accessible breakdown of the existing policy and structure, and an outline of all available support. | Matt Green (Head of Employee Relations and HR Business Partnering), Catherine Cox (Staff Health and Wellbeing Lead), Jo Mitchell (Staff Health and Wellbeing Lead), Sarah Stevens (HRBP) | Matt to adapt WRES guide for WDES and capability - update due at March 2023 review. Capability Policy due for review by Sarah by January 2023.
| 3.5 Review WDES capability cases from 2020/21, 2021/22 and 2022- to identify themes, patterns, and areas for improvement. | Matt Green (Head of Employee Relations and HR Business Partnering), Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead) | Cases where disability was declared on ESR have been reviewed, with Matt confident that they have been managed well, but noting prevalence in one CDS. Matt to write up findings in January 2023.
4. Percentage of Disabled staff compared to non-disabled staff experiencing harassment, bullying or abuse from patients/service users, their relatives or other members of the public, their managers, or other colleagues, and the percentage of Disabled staff compared to non-disabled staff saying that the last time they experienced harassment, bullying or abuse at work, they or a colleague reported it | 4.1 Launch a new anti-harassment/bullying/abuse campaign, linked to the Trust's ongoing work with Operation Cavell, including public-facing resources, e.g. posters, social media campaign materials. Focus on the behaviour not being acceptable, and the Trust supporting any staff member who wishes to pursue action. | Adam Graham (Violence Prevention and Reduction Manager), Dan Charlton (Chief Communications Officer) | Actions solely around Operation Cavell are on hold. Work has evolved into Reducing Racism in Services Group captured in WRES action plan.
| 4.2 Ensure leadership training includes procedure for managing incidents of harassment, bullying or abuse from patients/relatives/the public. | Adam Graham (Violence Prevention and Reduction Manager, Adrian Kerr (Interim Deputy Director of Workforce), Claire Webster (Interim Chief People Officer) | A victim support pack will be developed in Q4 of 2022/23, including signposting/guidance for supporters. Longer term actions will be identified for 2023/24.
| 4.3 Deliver Civility and Developing Better Relationships training, and three part Culture and Civility training programme. | Rachael Duke (Head of Charity), Claire Marr (Associate Director of OD and Talent Management) | Final cohort of Culture and Civility training programme opened for booking in September 2022. Civility and Developing Better Relationships training possibly moving in-house in 2023 following train the trainer sessions - eight delivered from October to December 2022 - but ICB-level training may also be an option. Claire to update at March 2023 review.
| 4.4 Support the Freedom to Speak Up Guardian to establish links with the staff networks. | Jacqui Buckley (Freedom to Speak Up Guardian), Sophie Lecky (Staff Network Coordinator) | Presentations/Q&As at five of the staff networks' meetings as of September 2022. Jacqui to attend LGBTQI+, Spirituality and Armed Forces Community meetings in early 2023.
| 4.5 Promote speaking up across the Trust, with a focus on bank staff, night staff, and other hard to reach groups. | Jacqui Buckley (Freedom to Speak Up Guardian) | Night staff reflective practice session attended in July 2022, and speaking up promoted at face-to-face Trust Inductions as of August 2022. FTSU Champions intranet page in draft as of December 2022, which will include photos and bios. FTSU success stories requested from bank workers, with update due at March 2023 review.
| 4.6 Establish and promote a clear pathway for staff experiencing discrimination from a manager/team leader or other colleagues. | Jo Mitchell (Staff Health and Wellbeing Lead), Catherine Cox (Staff Health and Wellbeing Lead), Adam Graham (Violence Prevention and Reduction Manager) | Will need to be revisited as originally to be based on campaign launch detailed in 4.1, adapted for workforce.
5. Percentage of Disabled staff compared to non-disabled staff believing that the Trust provides equal opportunities for career progression or promotion | 5.1 Develop a Talent Management Strategy that specifically aligns to the Trust's WDES priorities. | Carrie McEwan (Career Pathway Lead), Emily Sherman (Career Pathway Lead) | First draft of strategy delivered in April 2022. Emily Sherman - in post as of 10th October 2022 - will deliver the final strategy and its equality impact assessment (EIA) in early 2023. Update due at March 2023 review.
| 5.2 Update all courses on MyLearning to include accessibility information, via a dedicated Course Accessibility Project. | Hannah Thomas (System Expert Lead) | Accessibility information on core mandatory courses held either virtually or face to face live as of 2nd December 2022. Core mandatory e-learning courses will include accessibility information by January 2023. Work on the remaining 225 additional training courses will start mid-January 2023, but no estimated completion can be given at present due to reduced team capacity.
6. Percentage of Disabled staff compared to non-disabled staff saying that they have felt pressure from their manager to come to work, despite not feeling well enough to perform their duties | 6.1 Ensure new Occupational Health provision links directly to WDES action plan, and coordinates with other actions, e.g. centralised fund detailed in 8.1. | Adrian Kerr (Interim Deputy Director of Workforce), Jo Mitchell (Health and Wellbeing Lead), Catherine Gallop (Deputy Head of Facilities, Disability Staff Network Co-Chair) | Procurement process underway, but limited choice in contract provision will require monitoring. Catherine recommends appointment of a dedicated full time Occupational Health Project Manager to performance manage the contract provider, monitor KPIs, and centralise the recording of issues.
| 6.2 Review Sickness Absence and Attendance Management Policy to include disability leave. | Matt Green (Head of Employee Relations and HR Business Partnering), Nick McMaster (Staff Side Lead, Brighton and Hove) | The Sickness Absence and Attendance Management Policy has been updated without addition of disability leave to ensure compliance, so will need revision. Matt will use PWG on 12th January 2023 for a dedicated review, with update due at March 2023 review.
| 6.3 Include bespoke wellbeing module in new Leadership Plus course, including self-assessment and personalised goal-setting. | Claire Marr (Associate Director of OD and Talent Management), Catherine Cox (Health and Wellbeing Lead), Jo Mitchell (Health and Wellbeing Lead) | The wellbeing module explores balance, emotions and wellbeing planning. Programme launched November 2021, with approximately 65 in first cohort. Second cohort has started as of December 2022, with preparations for third cohort underway.
7. Percentage of Disabled staff compared to non-disabled staff saying that they are satisfied with the extent to which their organisation values their work | 7.1 Develop and submit a bid for the 2022 WDES Innovation Fund, for additional funding for projects supporting Disabled staff. | Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead), Sophie Lecky (Staff Network Coordinator), Chris Picknett (Workforce Equality, Diversity and Inclusion Project Manager) | Joint listening event including Disability Staff Network, Neurodivergent Staff Network and Valuing Lived Experience (VaLE) Mental Health Staff Network in June 2022, bid submitted in July 2022. Funding confirmed in September 2022, but delayed to November 2022. Project launched in November 2022 as detailed in 1.6.
| 7.2 Advise engagement with Disabled colleagues and relevant staff networks during the Equality Impact Assessment process, ensuring Disabled and neurodivergent colleagues are consulted on potential changes to the working environment, e.g. site moves and new digital solutions. | Jess Sandelson (Equality, Diversity, Inclusion and Human Rights Lead for People Using Services and Family and Friend Carers), Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead) | Revised Equality Impact Assessment paperwork, guidance and workshop programme delivered in August 2022. Senior Responsible Officer refresher courses originally due to start in January 2023, now delayed to February 2023 due to reduced capacity in team.
| 7.3 Celebrate relevant awareness days/weeks/months with signposting to regional/national events and resources, and producing original and accessible content. Encourage senior Disabled and neurodivergent staff to act as role models, e.g. by championing campaigns, sharing stories, producing videos or writing blog posts. | Dan Charlton (Chief Communications Officer), Sophie Lecky (Staff Network Coordinator), Fleur Goff-Beardsley (Workforce Equality, Diversity and Inclusion Project Manager, Disability Staff Network Co-Chair), Chris Picknett (Workforce Equality, Diversity and Inclusion Project Manager) | Awareness day/week/month promotion to be selected carefully to avoid awareness fatigue. Disability History Month was celebrated by the Disability Staff Network with a number of events, communications circulated Trust-wide, and signposting to external events and resources. Communications and EDI teams to work closely on delivering Innovation Fund work programme detailed in 1.6 and Scope's Get Inclusive work programme detailed in 2.6.
| 7.4 Ensure all internal and external Trust communications are accessible, including captions, alt text, transcripts etc. Ensure all new digital interventions meet our Web Content Accessibility Guidelines (WCAG) obligations, without using overlays. Change default Outlook font to Arial size 12 to embed accessibilty as standard practice. | Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead), Jess Sandelson (Equality, Diversity, Inclusion and Human Rights Lead for People Using Services and Family and Friend Carers), Dan Charlton (Chief Communications Officer), Sam Fisher (Digital Project Manager), Gurprit Pannu (Chief Digital Information Officer), Tina Giles (Director of Technology) | Following input from the Disability Staff Network, Chief Executive Officer webinars migrated from GoTo Webinar to Zoom as of August 2022 to improve accessibility. Outlook font change delivered on schedule in October 2022. New public website originally due in 2023, delivered ahead of schedule in November 2022. Communications team booked in for bespoke accessibility training with Emma in December 2022, now rescheduled for February 2023.
8. Percentage of Disabled staff saying that their employer has made adequate adjustment(s) to enable them to carry out their work | 8.1 Establish a centralised fund for reasonable adjustments, and provide support for staff throughout application, purchasing and installation processes. | Claire Webster (Interim Chief People Officer), Usman Niazi (Chief Finance Officer), Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead), Corin Ansted (Deputy Director of Finance), Chris Picknett (Workforce Equality, Diversity and Inclusion Project Manager) | Establishment of centralised fund for reasonable adjustments approved in July 2022. Emma confirmed as budget manager, with fund launched on 1st November 2022. Chris - in post as of 5th December 2022 - will manage fund administration. Fund will include dyslexia, dyscalculia and dyspraxia assessments.
| 8.2 Establish and promote a unified Trust-wide reasonable adjustments application, purchasing and installation process, to ensure parity of staff experience across teams and services. | Nia Thomas (Inclusive Recruitment Advisor), Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead), Chris Picknett (Workforce Equality, Diversity and Inclusion Project Manager), Dan Charlton (Chief Communications Officer) | Communications plan to be agreed upon draft of contract in 6.1 and revision of Recruitment and Selection Policy in 2.1. Nia created a factsheet for managers in November 2022, will develop a flow chart to include in manager training by January 2023, and will work on including reasonable adjustment notices and reminders on Trac. Update due at March 2023 review.
9. The staff engagement score for Disabled staff, compared to non-disabled staff, and "Has your Trust taken action to facilitate the voices of Disabled staff in your organisation to be heard?" (focused actions on 9a) | 9.1 Establish system to pay colleagues who attend staff network meetings outside of their working hours, to ensure representation from bank staff, part time staff, night staff etc. | Catherine Gallop (Disability Staff Network Co-Chair), Fleur Goff-Beardsley (Disability Staff Network Co-Chair), Sophie Lecky (Staff Network Coordinator), Usman Niazi (Chief Finance Officer), Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead) | Payment process for all networks agreed as of August 2022. Bank hours budget of up to £10,000 approved, Emma set up as budget manager, and central cost centre set up on schedule in September 2022. A template for an Executive Sponsor letter for staff attending network events within their working hours has also been approved.
| 9.2 Revise e-learning and face-to-face modules of the Equality, Diversity and Inclusion Induction training to include signposting to staff networks, and include a staff networks stall at face-to-face Induction marketplace. | Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead), Sophie Lecky (Staff Network Coordinator) | Revised e-learning module completed in July 2022. First face-to-face Induction using new module delivered in August 2022. Staff networks marketplace stalls included at all Trust Inductions from August 2022 onwards.
| 9.3 Improve the visibility and reach, and increase the membership of, the Disability Staff Network, the Neurodivergent Staff Network and the Valuing Lived Experience (VaLE) Mental Health Staff Network, measured through staff networks' benchmarking. | Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead), Sophie Lecky (Staff Network Coordinator) | Staff networks benchmarking launched on schedule and subject to quarterly review, with next benchmarking criteria review due January 2023. The three networks have a combined membership of 632 as of December 2022.
10. Percentage difference between the organisation’s Board membership and its overall workforce, disaggregated by voting membership of the Board and Executive membership of the Board, and comparing Disabled and non-disabled staff (focused actions) | 10.1 Build bespoke EDI training into Leadership Plus development programme. | Claire Marr (Associate Director of OD and Talent Management) | Learning topics include diversity and inclusion, psychological safety and understanding culture. Programme launched November 2021, with approximately 65 in first cohort. Second cohort has started as of December 2022, with preparations for third cohort underway.
| 10.2 Involve Inclusive Recruitment Advisor with all Board appointments, including liaising with external agencies. | Nia Thomas (Inclusive Recruitment Advisor), Adele D'Silva (Head of Workforce Supply) | Chief People Officer appointment announced in December 2022. Nia planning a case study analysis, due February 2023. Nia was also on the panel for the appointment of the agency to handle future Board appointments.
| 10.3 Specifically include Board throughout all stages of the WDES Innovation Fund work programme detailed in 1.6, including asking members to appear in the video, inviting them to speak at roadshow dates, and asking them to champion declaration/completion of all monitoring information across the Trust. | Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead), Claire Webster (Interim Chief People Officer), Chris Picknett (Workforce Equality, Diversity and Inclusion Project Manager), Dan Charlton (Chief Communications Officer) | Video and roadshow launch due in January 2023 as in 1.6. No Executive Directors could attend video production, but they will be involved throughout the video's launch and roadshow. Update due at March 2023 review.
| 10.4 Book senior leadership team, including Board members, onto Scope Get Inclusive workshops outlined in 2.6. | Nia Thomas (Inclusive Recruitment Advisor), Fleur Goff-Beardsley (Workforce Equality, Diversity and Inclusion Project Manager) | Scope programme will start 9th January 2023, as in 2.6.