## Sheet1
Next review date: 13th March 2023 |  | Green = on track, amber = requires monitoring, red = requires focused attention.
WRES indicator | Action | Responsible lead/leads | Progress
1. Percentage of staff in each of the Agenda for Change (AfC) bands 1-9 or Medical and Dental subgroups and Very Senior Managers (VSM) (including executive Board members) compared with the percentage of staff in the overall workforce | 1.1 Recruit a dedicated Inclusive Recruitment Advisor, who will conduct an end-to-end review of the recruitment process, including revising job description templates and the Trust's Recruitment and Selection Policy. | Adele D'Silva (Head of Workforce Supply) | Nia Thomas in post as of 1st August 2022.
| 1.2 Revise the Trust's image library to enhance visible diversity, and build meaningful role-modelling into all internal and external communications. | Dan Charlton (Chief Communications Officer) | Staff photos taken in May/June 2022. Image library rolled out in November 2022 with new public website. The library will be kept under review based on both workforce and public feedback.
| 1.3 Develop a Talent Management Strategy that specifically aligns to the Trust's WRES priorities. | Carrie McEwan (Career Pathway Lead), Emily Sherman (Career Pathway Lead) | First draft of strategy delivered in April 2022. Emily Sherman - in post as of 10th October 2022 - will deliver the final strategy and its equality impact assessment (EIA) in early 2023. Update due at March 2023 review.
| 1.4 Analyse data around apprenticeship uptake from ethnic minority groups, and review apprenticeships offer to encourage applications accordingly. | Stacey Killon (Workforce Transformation Manager for Apprenticeships), Nia Thomas (Inclusive Recruitment Advisor), Georgina Hawes (Leadership and Talent Coordinator), Sophie Lecky (Interim Ethnic Minority Staff Network Chair) | Snapshot data review showed staff from ethnic minority groups are underrepresented in apprenticeship uptake, including apprentices in learning, those taking breaks in learning, and those awaiting apprenticeship enrolment in September. Stacey to link in with Nia, George and Sophie to identify next steps. No update at December 2022 review.
| 1.5 Use the Psychology and Psychological Therapists (PPT) team as an example of good practice and source of ongoing learning. PPT initiatives include Health Education England (HEE)-funded bursaries for Assistant Psychologist posts (gateway to Clinical Psychologist roles), Trust-funded Psychology Undergraduate Student places and Postgraduate Volunteer bursaries, an external mentorship scheme, and a dedicated PPT Black and Ethnic Minorities Staff Forum. | Claire Bellezza (Project Team Manager for Psychological Professions), Nick Grey (Lead Consultant Psychologist), Claire Marr (Associate Director of OD and Talent Management) | 23 part time fixed term Assistant Psychologists have been recruited so far. Services have been asked to consider matching HEE funding in future, so posts can be full time. Interim internal report due in October 2022. £40,000 has been secured for bursaries for students starting in September and October, with internal report due in November 2022. External mentoring is aimed at Band 5-8a staff, with internal report due in October 2022. Reports to be shared with Claire Marr, for cascading as appropriate. No update at December 2022 review.
2. Relative likelihood of white applicants being appointed from shortlisting across all posts compared to BME applicants (focused actions) | 2.1 Revise the Trust's standard job advert wording, job description templates and Recruitment and Selection Policy to encourage a diverse range of applicants and remove potential barriers for applicants from marginalised groups. | Nia Thomas (Inclusive Recruitment Advisor) | Updated advert wording and job description templates to be uploaded onto new dedicated intranet page by end of December 2022, with further revisions likely after start of Scope programme in January 2023. Initial policy rewrite on track for January 2023, with a second version including new manager training/materials expected in April/May 2023.
| 2.2 Ensure all recruitment campaigns use appropriate imagery and language, to encourage a diverse range of applicants. | Nia Thomas (Inclusive Recruitment Advisor), Dan Charlton (Chief Communications Officer) | All new recruitment campaigns are using the updated image library as of November 2022. Nia and the Talent Attraction team are working closely with the Communications team to ensure alignment.
| 2.3 Include Experts by Experience (EbEs) on interview and stakeholder panels, and further increase the diversity of panels overall, with a focus on values-based interview techniques. | Elaine Colomberg (Interim Director of People Participation), Alex Garner (People Participation Lead), Nia Thomas (Inclusive Recruitment Advisor) | EbE panel representation is in place across the Trust, with Elaine and Alex working on materials for recruiting managers to standardise experience. Nia has included diversification of panels - not just the inclusion of EbEs - in new draft Recruitment and Selection Policy. Update due at March 2023 review.
| 2.4 Adopt Trust-wide values-based interview techniques as part of manager training, including a set of equality, diversity and inclusion (EDI) questions for panels to use. | Nia Thomas (Inclusive Recruitment Advisor) | EDI questions for Board and for bands 2-8a uploaded to intranet in September 2022. Training pilot initially due in January 2023 but delayed slightly as remit has expanded to include more of recruitment process. Pilot now due March 2023.
| 2.5 Expand appointment options beyond structured interviews, to include work experience, work trials and supported employment. | Nia Thomas (Inclusive Recruitment Advisor) | Details to be included in revised Recruitment and Selection Policy, with initial draft due January 2023. Adele and Nia have met to explore additional options, e.g. guaranteed interview scheme.
3. Relative likelihood of BME staff entering the formal disciplinary process compared to white staff | 3.1 Provide mediation training to service representatives. | Claire Marr (Associate Director of OD and Talent Management), Adam Graham (Violence Prevention and Reduction Manager) | Cohorts 1, 2 and 3 delivered in September, October and November 2022, but no further cohorts planned due to business continuity. Claire is working with Adam to explore restorative justice training, and Integrated Care Board (ICB) training is also in early planning stages. Update due at March 2023 review.
| 3.2 Provide equality, diversity and inclusion (EDI) and unconscious bias training to Employee Relations team. | Claire Marr (Associate Director of OD and Talent Management), Matt Green (Head of Employee Relations and HR Business Partnering), Claire Webster (Interim Chief People Officer) | Matt to discuss with HRBPs following December 2022 review, and Claire and Matt to discuss in-house delivery - considering business continuity - to HRBPs, managers and investigating officers. Update due at March 2023 review.
| 3.3 Capture data on issues that were resolved without formal processes, to identify successes of, and breakdowns of, informal processes. | Matt Green (Head of Employee Relations and HR Business Partnering), Claire Webster (Interim Chief People Officer) | A bespoke database cannot currently be funded, but an interim measure - using a centralised tracker that also captures informal data - is due by end of January 2023, with the caveat that this is a short term solution.
| 3.4 Develop a guide for staff entering the formal disciplinary process, outlining all available support. | Matt Green (Head of Employee Relations and HR Business Partnering), Catherine Cox (Staff Health and Wellbeing Lead), Jo Mitchell (Staff Health and Wellbeing Lead) | Staff side reviewed and approved the guide in October 2022.
4. Relative likelihood of white staff accessing non-mandatory training and continuing professional development (CPD) compared to BME staff | 4.1 Run focus groups with staff from ethnic minority groups, to establish barriers to accessing training and development opportunities, promote career conversations, encourage staff from ethnic minority groups to train as career coaches, and promote speaking up. | Claire Marr (Associate Director of OD and Talent Management), Emma Mendes da Costa (Workforce EDI Lead), Dan Charlton (Chief Communications Officer), Stacey Killon (Workforce Transformation Manager for Apprenticeships), Georgina Hawes (Leadership and Talent Coordinator and Freedom to Speak Up Champion) | Three focus groups run as of December 2022, including one with night staff at Mill View Hospital. More focus groups planned for 2023, with George to review findings and collate themes.
| 4.2 Develop strategies to support staff from ethnic minority groups, based on focus group findings. | Claire Marr (Associate Director of OD and Talent Management), Carrie McEwan (Career Pathway Lead) | Initially due end of December 2022, with deadline extended to include additional focus groups in 2023. George has also been promoting speaking up - in her role as Freedom to Speak Up Champion - as a way for attendees to provide further feedback outside of the focus group sessions.
5. Percentage of staff experiencing harassment, bullying or abuse from patients, relatives or the public in the last 12 months (focused actions) | 5.1 Launch a new anti-harassment/bullying/abuse campaign, linked to the Trust's ongoing work with Operation Cavell, including public-facing resources, e.g. posters, social media campaign materials. Focus on the behaviour not being acceptable, and the Trust supporting any staff member who wishes to pursue action. | Adam Graham (Violence Prevention and Reduction Manager), Dan Charlton (Chief Communications Officer), Hinal Chudasama (Lead Nurse for Nursing Standards and Safety) | Action has evolved beyond initial campaign due October 2022, encompassing a new dedicated Reducing Racism in Services Group led by Hinal, which will co-produce an intranet page, resources for staff, and new service user-facing and staff-facing campaign materials. Update due at March 2023 review.
| 5.2 Ensure leadership training includes procedure for managing incidents of harassment, bullying or abuse from patients/relatives/the public. | Adam Graham (Violence Prevention and Reduction Manager, Adrian Kerr (Interim Deputy Director of Workforce), Claire Webster (Interim Chief People Officer), Hinal Chudasama (Lead Nurse for Nursing Standards and Safety) | A victim support pack will be developed in Q4 of 2022/23, including signposting/guidance for supporters. Longer term actions will be identified for 2023/24.
| 5.3 Revise Staff in Mind service offer, to increase uptake by staff from ethnic minority groups. | Dan Charlton (Chief Communications Officer) | New messaging, imagery and website design produced following extensive consultation with staff from ethnic minority groups regarding the current service offer. Staff in Mind are running two webinars in January 2023 sharing their research, and providing training on inclusive leadership and supporting ethnically diverse staff.
6. Percentage of staff experiencing harassment, bullying or abuse from staff in the last 12 months | 6.1 Deliver Civility and Developing Better Relationships training, and three part Culture and Civility training programme. | Rachael Duke (Head of Charity), Claire Marr (Associate Director of OD and Talent Management) | Final cohort of Culture and Civility training programme opened for booking in September 2022. Civility and Developing Better Relationships training possibly moving in-house in 2023 following train the trainer sessions - eight delivered from October to December 2022 - but ICB-level training may also be an option. Claire to update at March 2023 review.
| 6.2 Deliver anti-racism training to Trust staff, and NHS and third sector partner staff across Sussex. | Rachael Duke (Head of Charity) | Training funded by Heads On. First session delivered July 2022, with further sessions offered from October to December 2022 in West Sussex, East Sussex and Brighton and Hove.
7. Percentage of staff believing that the Trust provides equal opportunities for career progression or promotion (focused actions) | 7.1 Support eligible colleagues to apply to national Stepping Up and Ready Now schemes. | Claire Marr (Associate Director of OD and Talent Management) | Stepping Up and Ready Now programmes now unlikely to restart in 2022/23 but positive action is now part of local discussions for the South East. Main contact is Sandra Elsenussi from SELA, who will update Claire.
| 7.2 Engage with and scope interventions to support night staff - a high number of whom are from ethnic minority groups - to strengthen links with corporate services. | Rachael Duke (Head of Charity) | Charitable funding bid for Band 6 Project Manager submitted in April 2022. Decision originally expected in July 2022, but funding approved and awarded in November 2022. Update due at March 2023 review.
| 7.3 Provide tailored career support to specialty and specialist grade (SAS) doctors - a high number of whom are from ethnic minority groups - via an SAS Advocate and the medical leadership and medical education teams. | Susan Hamilton (SAS Advocate and Freedom to Speak Up Champion) | Signposting to support and opportunities is ongoing, as is identifying and addressing barriers. SAS doctors surveyed in June 2022, with development day in November 2022.
8. Percentage of staff experiencing discrimination at work from their manager/team leader or other colleagues in the last 12 months (focused actions) | 8.1 Support the Freedom to Speak Up Guardian to establish links with the staff networks. | Jacqui Buckley (Freedom to Speak Up Guardian), Sophie Lecky (Staff Network Coordinator) | Presentations/Q&As at five of the staff networks' meetings as of September 2022. Jacqui to attend LGBTQI+, Spirituality and Armed Forces Community meetings in early 2023.
| 8.2 Promote speaking up across the Trust, with a focus on bank staff, night staff, and other hard to reach groups. | Jacqui Buckley (Freedom to Speak Up Guardian) | Night staff reflective practice session attended in July 2022, and speaking up promoted at face-to-face Trust Inductions as of August 2022. FTSU Champions intranet page in draft as of December 2022, which will include photos and bios. FTSU success stories requested from bank workers, with update due at March 2023 review.
| 8.3 Draft an Anti-Racism Policy to clearly communicate the Trust's proactive anti-racist stance. | Adrian Kerr (Interim Director Deputy of Workforce) | Initial outline completed as of September 2022. First draft to be taken to staff networks, the Sussex Race Equality Transformation Board, and staff side at Policy Working Group on 13th October 2022. Aiming for ratification at Trust Partnership Forum in January 2023.
| 8.4 Curate a programme of events for Black History Month in partnership with the Ethnic Minority Staff Network, and share events with NHS Sussex colleagues, to increase the visibility of staff from ethnic minority groups and affirm the Trust's anti-racist position. | Sophie Lecky (Staff Network Coordinator, Interim Ethnic Minority Staff Network Chair), Dan Charlton (Chief Communications Officer) | Events held throughout October 2022, including external speakers, staff stories, and a forum with Gurprit Pannu, the Ethnic Minority Staff Network's Executive Sponsor and Chief Digital and Information Officer. Schedule shared with NHS Sussex team. Network engagement has increased, and allies are invited to attend network meetings once a quarter. Network membership has increased to 172 as of December 2022.
9. BME Board membership | 9.1 Build bespoke EDI training into Leadership Plus development programme. | Claire Marr (Associate Director of OD and Talent Management) | Learning topics include diversity and inclusion, psychological safety and understanding culture. Programme launched November 2021, with approximately 65 in first cohort. Second cohort has started as of December 2022, with preparations for third cohort underway.
| 9.2 Involve Inclusive Recruitment Advisor with all Board appointments, including liaising with external agencies. | Nia Thomas (Inclusive Recruitment Advisor), Adele D'Silva (Head of Workforce Supply) | Chief People Officer appointment announced in December 2022. Nia is planning a case study analysis, due February 2023. Nia was also on the panel for the appointment of the agency to handle future Board appointments.