## Sheet1
Next review date: 12th June 2023 |  | Green = on track, amber = requires monitoring, red = requires focused attention.
WDES metric | Action | Responsible lead/leads | Progress
1. Percentage of Disabled staff in each of the Agenda for Change Bands 1-9, and VSM, compared to the percentage of staff in the overall workforce (focused actions) | 1.1 Establish targets and timeline for moving from Disability Confident Employer (Level 2) to Disability Confident Leader (Level 3), following revision of Recruitment and Selection Policy. | Nia Thomas (Inclusive Recruitment Advisor) | Revised Recruitment and Selection Policy now due end of April 2023. Update on submission of Disability Confident Leader validation template due at June 2023 review.
| 1.2 Analyse data around apprenticeship uptake from Disabled applicants/colleagues, and review apprenticeships offer to encourage applications accordingly. | Stacey Killon (Workforce Transformation Manager for Apprenticeships), Nia Thomas (Inclusive Recruitment Advisor) | There are now regular communications about apprenticeship opportunities, via emails, flyers, posters etc., and opportunities are also cascaded through the staff network groups. Apprenticeship data has now been compared to both ESR data and Sussex demographic data, with Nia and Stacey to meet and discuss additional actions. Update due at June 2023 review.
| 1.3 Deliver WDES Innovation Fund work programme of bespoke video and roadshow designed to improve declaration rates, following successful bid for Declaration Rates Award. | Chris Picknett (Workforce Equality, Diversity and Inclusion Project Manager), Dan Charlton (Chief Communications Officer) | Programme launched in November 2022 after slight funding delay. Roadshow visited six Trust sites in February 2023, with more dates planned after final report. Final report to NHSE WDES team due in April 2023.
2. Relative likelihood of non-disabled staff compared to Disabled staff being appointed from shortlisting across all posts | 2.1 Revise the Trust's recruitment and selection processes to encourage a diverse range of applicants, and remove potential barriers for applicants from marginalised groups. | Nia Thomas (Inclusive Recruitment Advisor) | Policy rewrite slightly delayed from January 2023 start, but started as of February 2023 and submission - including equality impact assessment - planned for end of April 2023 as per 1.1. A revised second version, expanded to include new manager training/materials, will be available by Q2, July 2023. Candidate experience survey to attach to Trac emails due end of May 2023.
| 2.2 Create supporting job packs and accessible interview processes for lived experience roles, e.g. peer support roles, in line with the Trust's 2022/23 breakthrough objective of employing more staff with lived experience. | Adele D'Silva (Head of Workforce Supply), Sarah Livermore (Peer Support Lead), Nia Thomas (Inclusive Recruitment Advisor) | The packs and processes will be designed to give applicants confidence in using their lived experience in their applications, and clarity on how their lived experience will be used in the roles. Nia is now working on candidate-facing documents with Sarah, and identifying further actions from the Peer Support Strategy, with a further update due at the June 2023 review.
| 2.3 Include Experts by Experience (EbEs) on interview and stakeholder panels, to increase focus on values-based interview techniques. | Elaine Colomberg (Interim Director of People Participation), Alex Garner (People Participation Lead), Nia Thomas (Inclusive Recruitment Advisor) | EbE panel representation is in place across the Trust, and Elaine and Alex have developed materials to support recruiting managers to that effect. Nia has included diversification of panels - not just the inclusion of EbEs - in the draft Recruitment and Selection Policy, and is collating EbE-focused manager guidance with general recruiting manager guidance. Update due at June 2023 review.
| 2.4 Adopt Trust-wide values-based interview techniques as part of manager training, including a set of equality, diversity and inclusion (EDI) questions for panels to use. | Nia Thomas (Inclusive Recruitment Advisor) | EDI questions for Board and for bands 2-8a uploaded to intranet in September 2022. Training pilot initially due in January 2023, but rollout - including both an overview and more in-depth workshops - will be in place by June 2023 review.
| 2.5 Expand appointment options beyond structured interviews, to include work experience, work trials and supported employment. | Nia Thomas (Inclusive Recruitment Advisor), Claire Webster (Interim Chief People Officer) | Details to be included in revised Recruitment and Selection Policy as per 1.1 and 2.1. Adele and Nia are exploring additional options, including alternative assessment methods, guaranteed interview schemes and reaching out to local supported employment teams.
| 2.6 Roll out disability awareness training via Scope's Get Inclusive programme. To be overseen by Project Manager post created through job carving, with the rollout supported by the Education and Training team. Package includes inclusive recruitment workshops for HR Advisors and recruiting managers, toolkits/resources, and the use of Scope's Job Board. | Nia Thomas (Inclusive Recruitment Advisor), Fleur Goff-Beardsley (Workforce Equality, Diversity and Inclusion Project Manager), Claire Marr (Associate Director of OD and Talent Management) | Scope contract started on 9th January 2023. First awareness sessions booked in for March and April 2023. Following an initial review of SPFT, Scope are due to provide a report in Q1 of 2023/24.
3. Relative likelihood of Disabled staff compared to non-disabled staff entering the formal capability process, as measured by entry into the formal capability procedure (focused actions) | 3.1 Provide mediation training to service representatives. | Claire Marr (Associate Director of OD and Talent Management), Matt Green (Head of Employee Relations and HR Business Partnering) | Three cohorts of Resolution Facilitator Training delivered in September, October and November 2022.
| 3.2 Provide equality, diversity and inclusion (EDI), unconscious bias training and Scope training detailed in 2.6 to Employee Relations team. | Claire Marr (Associate Director of OD and Talent Management), Matt Green (Head of Employee Relations and HR Business Partnering), Claire Webster (Interim Chief People Officer) | Employee Relations team happy to undertake EDI and unconscious bias training. Claire and Matt to meet to discuss requirements and commissioning. Training would be prioritised for Investigating Officers (including new Bank pool) in May 2023. Update initially due at March review, now due at June 2023 review. Scope training - first dates in March and April as per 2.6- to be cascaded to team.
| 3.3 Capture data on issues that were resolved with informal processes. | Matt Green (Head of Employee Relations and HR Business Partnering), Claire Webster (Interim Chief People Officer) | A bespoke database cannot currently be funded, but an interim measure - using a centralised tracker that also captures informal data - was due by end of January 2023. Tracker produced but not yet populated - will be by end of April 2023.
| 3.4 Develop a guide for staff entering the formal capability process, including an accessible breakdown of the existing policy and structure, and an outline of all available support. | Matt Green (Head of Employee Relations and HR Business Partnering), Catherine Cox (Staff Health and Wellbeing Lead), Jo Mitchell (Staff Health and Wellbeing Lead) | Staff side reviewed and approved the guide in October 2022. Guide finalised and in use as of March 2023.
| 3.5 Review WDES capability cases from 2020/21, 2021/22 and 2022- to identify themes, patterns, and areas for improvement. | Matt Green (Head of Employee Relations and HR Business Partnering), Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead) | Cases where disability was declared on ESR have been reviewed, with Matt confident that they have been managed well, but noting prevalence in one CDS. Findings have been shared with Emma as of March 2023, noting to improve recording of cases, and that regular and effective supervisions and the centralised reasonable adjustments fund should address many issues.
4. Percentage of Disabled staff compared to non-disabled staff experiencing harassment, bullying or abuse from patients/service users, their relatives or other members of the public, their managers, or other colleagues, and the percentage of Disabled staff compared to non-disabled staff saying that the last time they experienced harassment, bullying or abuse at work, they or a colleague reported it | 4.1 Launch a new anti-harassment/bullying/abuse campaign, linked to the Trust's ongoing work with Operation Cavell, including public-facing resources, e.g. posters, social media campaign materials. Focus on the behaviour not being acceptable, and the Trust supporting any staff member who wishes to pursue action. | Adam Graham (Violence Prevention and Reduction Manager), Dan Charlton (Chief Communications Officer) | Actions solely around Operation Cavell are on hold. Work has evolved into Reducing Racism in Services Group (RRISG) captured in WRES action plan. First Operation Cavell relaunch meeting now due end of March 2023.
| 4.2 Ensure leadership training includes procedure for managing incidents of harassment, bullying or abuse from patients/relatives/the public. | Adam Graham (Violence Prevention and Reduction Manager, Adrian Kerr (Interim Deputy Director of Workforce), Claire Webster (Interim Chief People Officer) | A victim support pack will be developed in Q4 of 2022/23, including signposting/guidance for supporters. Longer term actions will be identified for 2023/24. No update at March 2023 review.
| 4.3 Scope civility and respect training package with NHS Sussex (ICB). | Claire Marr (Associate Director of OD and Talent Management), Adam Graham (Violence Prevention and Reduction Manager) | Meeting with preferred provider w/c 13th March to discuss. Update due at June 2023 review.
| 4.4 Support the Freedom to Speak Up Guardian to establish links with the staff networks. | Jacqui Buckley (Freedom to Speak Up Guardian), Courtney Williams (Staff Network Coordinator) | Work is ongoing: Jacqui attended the Women's Network's International Women's Day celebrations in March 2023 and is due to present to the Armed Forces Community Staff Network in May 2023. Courtney starting in post on 6th April 2023.
| 4.5 Promote speaking up across the Trust, including to bank staff, night staff, and other groups facing barriers to speaking up. | Jacqui Buckley (Freedom to Speak Up Guardian) | Night staff reflective practice session attended in July 2022, and speaking up promoted at face-to-face Trust Inductions as of August 2022. FTSU Champions intranet page has been developed and published as of March 2023 review, with 22 Champions across the Trust. Jacqui will be collecting monitoring information as of April 2023.
| 4.6 Establish and promote a clear pathway for staff experiencing discrimination from a manager/team leader or other colleagues. | Adam Graham (Violence Prevention and Reduction Manager), Matt Green (Head of Employee Relations and HR Business Partnering), Jacqui Buckley (Freedom to Speak Up Guardian), Catherine Cox (Staff Health and Wellbeing Lead), Jo Mitchell (Staff Health and Wellbeing Lead) | Will need to be revisited as originally to be based on campaign launch detailed in 4.1, adapted for workforce. No update at March 2023 review.
5. Percentage of Disabled staff compared to non-disabled staff believing that the Trust provides equal opportunities for career progression or promotion | 5.1 Develop a Talent Management Strategy that specifically aligns to the Trust's WDES priorities. | Emily Sherman (Career Pathway Lead) | Emily Sherman in post as of 10th October 2022. Strategy is in draft and will be shared with the staff networks for feedback by the end of March 2023. Feedback will be incorporated into the final draft by June review meeting, ahead of ratification at Board.
| 5.2 Update all courses on MyLearning to include accessibility information, via a dedicated Course Accessibility Project. | Hannah Thomas (System Expert Lead) | Accessibility information on core mandatory courses held either virtually or face to face live as of 2nd December 2022. Core mandatory e-learning courses updated to include accessibility information by end of December 2022. Work on the remaining 400+ additional training courses has started as planned, but no estimated completion can be given at present due to reduced team capacity.
6. Percentage of Disabled staff compared to non-disabled staff saying that they have felt pressure from their manager to come to work, despite not feeling well enough to perform their duties | 6.1 Ensure new Occupational Health provision links directly to WDES action plan, and coordinates with other actions, e.g. centralised fund detailed in 8.1. | Adrian Kerr (Interim Deputy Director of Workforce), Jo Mitchell (Health and Wellbeing Lead), Catherine Gallop (Deputy Head of Facilities, Disability Staff Network Co-Chair), Chris Picknett (Workforce Equality, Diversity and Inclusion Project Manager) | Optima confirmed as new provider as of 1st April 2023, with notice to staff about transfer of files sent out in March 2023. Chris linking in re: centralised reasonable adjustments fund (CRAF), catalogue of products/technology compatible with IT and Procurement, and provision of dyscalculia/dyslexia/dyspraxia assessments.
| 6.2 Review Sickness Absence and Attendance Management Policy to include disability leave. | Matt Green (Head of Employee Relations and HR Business Partnering), Nick McMaster (Staff Side Lead, Brighton and Hove) | The Sickness Absence and Attendance Management Policy has been updated without addition of disability leave to ensure compliance, so will need revision. Matt to extend PWG on 13th April to discuss disability leave and attendant Bradford score/payroll implications. Changes will require ratification at Trust Partnership Forum. Update due at June 2023 review.
7. Percentage of Disabled staff compared to non-disabled staff saying that they are satisfied with the extent to which their organisation values their work | 7.1 Advise engagement with Disabled colleagues and relevant staff networks during the Equality Impact Assessment process, ensuring Disabled and neurodivergent colleagues are consulted on potential changes to the working environment, e.g. site moves and new digital solutions. | Jess Sandelson (Equality, Diversity, Inclusion and Human Rights Lead for People Using Services and Family and Friend Carers), Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead) | Revised Equality Impact Assessment paperwork, guidance and workshop programme delivered in August 2022. Senior Responsible Officer refresher courses originally due to start in January 2023, now starting in April 2023 due to reduced capacity in team.
| 7.2 Celebrate relevant awareness days/weeks/months with signposting to regional/national events and resources, and producing original and accessible content. Encourage senior Disabled and neurodivergent staff to act as role models, e.g. by championing campaigns, sharing stories, producing videos or writing blog posts. | Dan Charlton (Chief Communications Officer), Courtney Williams (Staff Network Coordinator), Fleur Goff-Beardsley (Workforce Equality, Diversity and Inclusion Project Manager, Disability Staff Network Co-Chair), Chris Picknett (Workforce Equality, Diversity and Inclusion Project Manager) | Communications and EDI teams are working closely on delivering Innovation Fund work programme detailed in 1.3 and Scope's Get Inclusive work programme detailed in 2.6. As of March 2023 the Disability Staff Network are designing a survey to circulate to members re: which awareness events to focus on in 2023/24. Update due at June 2023 review.
| 7.3 Ensure all internal and external Trust communications are accessible, including captions, alt text, transcripts etc. Ensure all new digital interventions meet our Web Content Accessibility Guidelines (WCAG) obligations, without using overlays. Change default Outlook font to Arial size 12 to embed accessibilty as standard practice. | Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead), Jess Sandelson (Equality, Diversity, Inclusion and Human Rights Lead for People Using Services and Family and Friend Carers), Dan Charlton (Chief Communications Officer), Sam Fisher (Digital Project Manager), Gurprit Pannu (Chief Digital Information Officer), Tina Giles (Director of Technology) | Following input from the Disability Staff Network, Chief Executive Officer webinars migrated from GoTo Webinar to Zoom as of August 2022 to improve accessibility. Outlook font change delivered on schedule in October 2022. New public website originally due in 2023, delivered ahead of schedule in November 2022. Emma delivered accessible communications training to Communications team in February 2023 and is providing ongoing accessibility consultation. WDES Innovation Fund video has captions, audio description and BSL interpretation.
8. Percentage of Disabled staff saying that their employer has made adequate adjustment(s) to enable them to carry out their work | 8.1 Establish a centralised fund for reasonable adjustments, and provide support for staff throughout application, purchasing and installation processes. | Claire Webster (Interim Chief People Officer), Usman Niazi (Chief Finance Officer), Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead), Corin Ansted (Deputy Director of Finance), Chris Picknett (Workforce Equality, Diversity and Inclusion Project Manager) | Centralised reasonable adjustments fund (CRAF) established as of 1st November 2022, with Emma as budget manager and Chris handling day-to-day administration. Fund includes dyslexia, dyscalculia and dyspraxia assessments until new Occupational Health contract starts in April 2023. CRAF due dedicated intranet page by end of April 2023. Chris also working on rollout of Mindview software to support neurodivergent colleagues, with update due at June 2023 review.
| 8.2 Establish and promote a unified Trust-wide reasonable adjustments application, purchasing and installation process, to ensure parity of staff experience across teams and services. | Nia Thomas (Inclusive Recruitment Advisor), Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead), Chris Picknett (Workforce Equality, Diversity and Inclusion Project Manager), Dan Charlton (Chief Communications Officer) | Full communications plan to be agreed upon start of new Occupational Health provision in 6.1 and revision of Recruitment and Selection Policy in 1.1. Nia has created a factsheet for managers, and has editied all automated Trac emails to managers and candidates as of February 2023. Update due at June 2023 review.
9. The staff engagement score for Disabled staff, compared to non-disabled staff, and "Has your Trust taken action to facilitate the voices of Disabled staff in your organisation to be heard?" (focused actions on 9a) | 9.1 Establish system to pay colleagues who attend staff network meetings outside of their working hours, to ensure representation from bank staff, part time staff, night staff etc. | Catherine Gallop (Disability Staff Network Co-Chair), Fleur Goff-Beardsley (Disability Staff Network Co-Chair), Usman Niazi (Chief Finance Officer), Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead), Courtney Williams (Staff Network Coordinator) | Payment system has been established and refined, and will be managed by Courtney, starting in post on 6th April 2023.
| 9.2 Revise e-learning and face-to-face modules of the Equality, Diversity and Inclusion Induction training to include signposting to staff networks, and include a staff networks stall at face-to-face Induction marketplace. | Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead) | Revised e-learning module of Induction completed in July 2022. First face-to-face Induction using new module delivered in August 2022. Staff networks marketplace stalls included at Trust Inductions from August 2022 onwards. As of March 2023, Emma also offers bespoke versions of the mandatory EDHR e-learning for staff members who find MyLearning inaccessible.
| 9.3 Improve the visibility and reach, and increase the membership of, the Disability Staff Network, the Neurodivergent Staff Network and the Valuing Lived Experience (VaLE) Mental Health Staff Network, measured through staff networks' benchmarking. | Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead), Courtney Williams (Staff Network Coordinator) | Staff networks benchmarking launched on schedule and subject to quarterly review, with benchmarking criteria last reviewed in January 2023. The three networks have a combined membership of 632 as of December 2022.
10. Percentage difference between the organisation’s Board membership and its overall workforce, disaggregated by voting membership of the Board and Executive membership of the Board, and comparing Disabled and non-disabled staff (focused actions) | 10.1 Involve Inclusive Recruitment Advisor with all Board appointments, including liaising with external agencies. | Nia Thomas (Inclusive Recruitment Advisor), Adele D'Silva (Head of Workforce Supply) | Nia was on the panel for appointment of the agency to handle future Board appointments, and is also planning a case study analysis of the Chief People Officer appointment in December 2022 - currently waiting on feedback from the recruitment agency. Next step is the development of guidance on panel diversity for the appointment of the Trust's new Chief of Staff.
| 10.2 Specifically include Board throughout all stages of the WDES Innovation Fund work programme detailed in 1.3, including asking members to appear in the video, inviting them to speak at roadshow dates, and asking them to champion declaration/completion of all monitoring information across the Trust. | Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead), Claire Webster (Interim Chief People Officer), Chris Picknett (Workforce Equality, Diversity and Inclusion Project Manager), Dan Charlton (Chief Communications Officer) | No one available to attend video production or roadshow dates. Video launched in March 2023, shared in Trust-wide and external comms, and has been shared with Board members with a request to cascade and promote.
| 10.3 Book senior leadership team, including Board members, onto Scope Get Inclusive workshops outlined in 2.6. | Nia Thomas (Inclusive Recruitment Advisor), Fleur Goff-Beardsley (Workforce Equality, Diversity and Inclusion Project Manager) | Scope programme started on 9th January 2023, as in 2.6. Board members will be encouraged to attend the first workshop dates in March and April 2023. Usman Niazi, in his capacity as Executive Sponsor of the Disability Staff Network, is promoting the programme at Executive level.