## Sheet1
Next review date: 12th June 2023 |  | Green = on track, amber = requires monitoring, red = requires focused attention.
WRES indicator | Action | Responsible lead/leads | Progress
1. Percentage of staff in each of the Agenda for Change (AfC) bands 1-9 or Medical and Dental subgroups and Very Senior Managers (VSM) (including executive Board members) compared with the percentage of staff in the overall workforce | 1.1 Develop a Talent Management Strategy that specifically aligns to the Trust's WRES priorities. | Emily Sherman (Career Pathway Lead) | Emily Sherman in post as of 10th October 2022. Strategy is in draft and will be shared with the staff networks for feedback by the end of March 2023. Feedback will be incorporated into the final draft by June review meeting, ahead of ratification at Board.
| 1.2 Improve advertisement and promotion of training and development opportunities, based on the findings of the focus groups detailed in 4.1. | Georgina Hawes (Leadership and Talent Coordinator), Xav Pittal (Ethnic Minority Staff Network Co-Chair), Anna Watson (Ethnic Minority Staff Network Co-Chair) | Focus group actions finalised in February 2023 include reducing reliance on email comms, training managers to ensure they signpost their teams to opportunities e.g. apprenticeships and career conversations, and training representatives speaking at staff network meetings.
| 1.3 Analyse data around apprenticeship uptake from ethnic minority groups, and review apprenticeships offer to encourage applications accordingly. | Stacey Killon (Workforce Transformation Manager for Apprenticeships), Nia Thomas (Inclusive Recruitment Advisor) | There are now regular communications about apprenticeship opportunities, via emails, flyers, posters etc. as per 1.2, and opportunities are also cascaded through the staff network groups. Apprenticeship data has now been compared to both ESR data and Sussex demographic data, with Nia and Stacey to meet and discuss additional actions. Update due at June 2023 review.
| 1.4 Use the Psychological Professions team as an example of good practice and source of ongoing learning. | Claire Bellezza (Project Team Manager for Psychological Professions), Nick Grey (Lead Consultant Psychologist), Claire Marr (Associate Director of OD and Talent Management), Neha Cattra (Psychological Professions Education and Training Specialist) | Health Education England funding has been secured for a further 12 Assistant Psychologist (AP) posts, five of which will be full time via matched funding. Five posts recruited to already, with a further round of recruitment due in April 2023. Other initiatives include internal bursaries, internal mentoring for APs, and external mentoring for B5-8a staff. Internal reports initially due in October 2022 have not been completed due to clinical pressures, but Neha is taking over the workstreams, with reports now due end of May 2023. Reports to be shared with Claire Marr, for cascading as appropriate.
2. Relative likelihood of white applicants being appointed from shortlisting across all posts compared to BME applicants (focused actions) | 2.1 Revise the Trust's Recruitment and Selection Policy to encourage a diverse range of applicants and remove potential barriers for applicants from marginalised groups. | Nia Thomas (Inclusive Recruitment Advisor) | Policy rewrite slightly delayed from January 2023 start, but started as of February 2023 and submission - including equality impact assessment - planned for end of April 2023. A revised second version, expanded to include new manager training/materials, will be available by Q2, July 2023.
| 2.2 Include Experts by Experience (EbEs) on interview and stakeholder panels, and further increase the diversity of panels overall, with a focus on values-based interview techniques. | Elaine Colomberg (Interim Director of People Participation), Alex Garner (People Participation Lead), Nia Thomas (Inclusive Recruitment Advisor) | EbE panel representation is in place across the Trust, and Elaine and Alex have developed materials to support recruiting managers to that effect. Nia has included diversification of panels - not just the inclusion of EbEs - in the draft Recruitment and Selection Policy, and is collating EbE-focused manager guidance with general recruiting manager guidance. Update due at June 2023 review.
| 2.4 Adopt Trust-wide values-based interview techniques as part of manager training, including a set of equality, diversity and inclusion (EDI) questions for panels to use. | Nia Thomas (Inclusive Recruitment Advisor) | EDI questions for Board and for bands 2-8a uploaded to intranet in September 2022. Training pilot initially due in January 2023, but rollout - including both an overview and more in-depth workshops - will be in place by June 2023 review.
| 2.5 Expand appointment options beyond structured interviews, to include work experience, work trials and supported employment. | Nia Thomas (Inclusive Recruitment Advisor) | Details to be included in revised Recruitment and Selection Policy as per 2.1. Adele and Nia are exploring additional options, including alternative assessment methods, guaranteed interview schemes and reaching out to local supported employment teams.
3. Relative likelihood of BME staff entering the formal disciplinary process compared to white staff | 3.1 Provide mediation training to service representatives. | Claire Marr (Associate Director of OD and Talent Management), Adam Graham (Violence Prevention and Reduction Manager) | Three cohorts of Resolution Facilitator Training delivered in September, October and November 2022.
| 3.2 Develop mediation flowchart to align with existing HR policies. | Claire Marr (Associate Director of OD and Talent Management) | In development with FTSU Guardian. Update due at June 2023 review.
| 3.3 Scope civility and respect training package with NHS Sussex (ICB). | Claire Marr (Associate Director of OD and Talent Management), Adam Graham (Violence Prevention and Reduction Manager) | Meeting with preferred provider w/c 13th March to discuss. Update due at June 2023 review.
| 3.4 Provide equality, diversity and inclusion (EDI) and unconscious bias training to Employee Relations team. | Claire Marr (Associate Director of OD and Talent Management), Matt Green (Head of Employee Relations and HR Business Partnering), Claire Webster (Interim Chief People Officer) | Employee Relations team happy to undertake training. Claire and Matt to meet to discuss requirements and commissioning. Training would be prioritised for Investigating Officers (including new Bank pool) in May 2023. Update initially due at March review, now due at June 2023 review.
| 3.5 Capture data on issues that were resolved with informal processes. | Matt Green (Head of Employee Relations and HR Business Partnering), Claire Webster (Interim Chief People Officer) | A bespoke database cannot currently be funded, but an interim measure - using a centralised tracker that also captures informal data - was due by end of January 2023. Tracker produced but not yet populated - will be by end of April 2023.
| 3.6 Develop a guide for staff entering the formal disciplinary process, outlining all available support. | Matt Green (Head of Employee Relations and HR Business Partnering), Catherine Cox (Staff Health and Wellbeing Lead), Jo Mitchell (Staff Health and Wellbeing Lead) | Staff side reviewed and approved the guide in October 2022. Guide finalised and in use as of March 2023.
4. Relative likelihood of white staff accessing non-mandatory training and continuing professional development (CPD) compared to BME staff | 4.1 Run focus groups with staff from ethnic minority groups, to establish barriers to accessing training and development opportunities, promote career conversations, encourage staff from ethnic minority groups to train as career coaches, and promote speaking up. | Claire Marr (Associate Director of OD and Talent Management), Stacey Killon (Workforce Transformation Manager for Apprenticeships), Georgina Hawes (Leadership and Talent Coordinator and Freedom to Speak Up Champion) | Focus groups were conducted by Georgina October 2022 onwards. Findings were collated and actions were identified: using alternative means for circulating training opportunities, working with managers - including appraisal training - to ensure they promote training opportunities, training representation at staff network meetings, training opportunities outside of core hours, and promotion of career conversations and coaches.
| 4.2 Develop strategies to support staff from ethnic minority groups, based on focus group findings. | Claire Marr (Associate Director of OD and Talent Management), Emily Sherman (Career Pathway Lead) | Initial actions outlined in 4.1. Update due at June 2023 review.
5. Percentage of staff experiencing harassment, bullying or abuse from patients, relatives or the public in the last 12 months (focused actions) | 5.1 Launch a new anti-harassment/bullying/abuse campaign, linked to the Trust's ongoing work with Operation Cavell, including public-facing resources, e.g. posters, social media campaign materials. Focus on the behaviour not being acceptable, and the Trust supporting any staff member who wishes to pursue action. | Adam Graham (Violence Prevention and Reduction Manager), Dan Charlton (Chief Communications Officer), Hinal Chudasama (Lead Nurse for Nursing Standards and Safety) | Action has evolved beyond initial campaign due October 2022, encompassing a new dedicated Reducing Racism in Services Group led by Hinal, which is co-producing an intranet page, resources for staff, and new service user-facing and staff-facing campaign materials. Update due at June 2023 review.
| 5.2 Tailor site and/or service-specific interventions based on wider Trust policies and procedures, using Langley Green as a pilot. | Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead), Bridget Mullany (Matron), Pallavi Bala (Principal Psychologist) | Fortnightly meetings established with leads, focusing on 1. improving incident reporting 2. staff support and 3. staff training. Site-specific interventions include public-facing messaging, signposting to opportunities e.g. Heads On Anti-Racism Training, and trialling support/engagement groups for night staff.
| 5.3 Ensure leadership training includes procedure for managing incidents of harassment, bullying or abuse from patients/relatives/the public. | Adam Graham (Violence Prevention and Reduction Manager, Adrian Kerr (Interim Deputy Director of Workforce), Claire Webster (Interim Chief People Officer), Hinal Chudasama (Lead Nurse for Nursing Standards and Safety), Hilary Charlton (Associate Director of OD and Leadership Development) | A victim support pack will be developed in Q4 of 2022/23, including signposting/guidance for supporters. Longer term actions will be identified for 2023/24. No update at March 2023 review.
6. Percentage of staff experiencing harassment, bullying or abuse from staff in the last 12 months | 6.1 Deliver anti-racism training to Trust staff, and NHS and third sector partner staff across Sussex. | Rachael Duke (Head of Charity) | Target reach of 900 across East and West Sussex. 140 have attended sessions to date, with nine more sessions planned for March-July 2023. Next steps are a Beyond Race symposium showcasing best practice and looking to the future, to be delivered summer 2023, and an organisational development programme for partners, to be delivered in 2023.
| 6.2 Expand comprehensive support package for international recruits to include cultural allyship training for teams, support for them to speak up, and safe spaces e.g. an international staff network. | Jackie Lake (International Recruitment Lead), Nia Thomas (Inclusive Recruitment Advisor), Adele D'Silva (Head of Workforce Supply), Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead), Jacqui Buckley (Freedom to Speak Up Guardian) | Leads met with preferred provider of cultural allyship training on 9th March. Jacqui to link in with Ethnic Minority Staff Network, meet with Chief Nurse, and reach out to international recruits via email and Trust-wide comms. Update due at June 2023 review.
7. Percentage of staff believing that the Trust provides equal opportunities for career progression or promotion (focused actions) | 7.1 Engage with and scope interventions to support night staff - a high number of whom are from ethnic minority groups - to strengthen links with corporate services. | Rachael Duke (Head of Charity), Catherine Cox (Health and Wellbeing Lead), Jo Mitchell (Health and Wellbeing Lead) | Charitable funding bid for post submitted in April 2022. Decision originally expected in July 2022, but funding approved and awarded in November 2022. Health and Wellbeing team actively recruiting the Band 6 Project Support Manager now, to be in post by June 2023 review.
| 7.2 Provide tailored career support to specialty and specialist grade (SAS) doctors - a high number of whom are from ethnic minority groups - via an SAS Advocate and the medical leadership and medical education teams. | Susan Hamilton (SAS Advocate and Freedom to Speak Up Champion) | Signposting to support and opportunities is ongoing, as is identifying and addressing barriers. SAS development days have restarted, with last in November 2022 and next due April 2023, with themes of ethnic diversity and neuorodivergence. As of December 2022 training has started for appraisers on the specific issues faced by SAS doctors. Group for new doctors established in December 2022 and meeting every two months. Next step is a new doctors induction pack, update due at June 2023 review.
| 7.3 Cascade relevant internal and external training and development opportunities - as per the actions outlined in 4.1 - to staff from ethnic minority groups, and support them to apply as required. | Claire Marr (Associate Director of OD and Talent Management), Xav Pittal (Ethnic Minority Staff Network Co-Chair), Anna Watson (Ethnic Minority Staff Network Co-Chair), Emma Mendes da Costa (Workforce Equality, Diversity and Inclusion Lead) | Signposting is established and ongoing, including linking to the South East Leadership Academy, e.g. Succeeding at Interviews Workshops for Minority Ethnic Women in March and April 2023.
8. Percentage of staff experiencing discrimination at work from their manager/team leader or other colleagues in the last 12 months (focused actions) | 8.1 Support the Freedom to Speak Up Guardian to establish links with the staff networks. | Jacqui Buckley (Freedom to Speak Up Guardian), Courtney Williams (Staff Network Coordinator) | Work is ongoing: Jacqui attended the Women's Network's International Women's Day celebrations in March 2023 and is due to present to the Armed Forces Community Staff Network in May 2023. Courtney starting in post on 6th April 2023.
| 8.2 Promote speaking up across the Trust, including to bank staff, night staff, and other groups facing barriers to speaking up. | Jacqui Buckley (Freedom to Speak Up Guardian) | Night staff reflective practice session attended in July 2022, and speaking up promoted at face-to-face Trust Inductions as of August 2022. FTSU Champions intranet page has been developed and published as of March 2023 review, with 22 Champions across the Trust. Jacqui will be collecting monitoring information as of April 2023.
| 8.3 Draft an Anti-Racism Policy to clearly communicate the Trust's proactive anti-racist stance. | Adrian Kerr (Interim Director Deputy of Workforce), Claire Webster (Interim Chief People Officer) | Initial outline completed as of September 2022. First draft to be taken to staff networks, the Sussex Race Equality Transformation Board, and staff side at Policy Working Group on 13th October 2022. Claire to take policy finalisation on in April 2023.
9. BME Board membership | 9.1 Involve Inclusive Recruitment Advisor with all Board appointments, including liaising with external agencies. | Nia Thomas (Inclusive Recruitment Advisor), Adele D'Silva (Head of Workforce Supply | Nia was on the panel for appointment of the agency to handle future Board appointments, and is also planning a case study analysis of the Chief People Officer appointment in December 2022 - currently waiting on feedback from the recruitment agency. Next step is the development of guidance on panel diversity for the appointment of the Trust's new Chief of Staff.
| 9.2 Keep diversity of interview and stakeholder panels for Board appointments under review, to bring a range of expertise and lived experiences to the appointment process. | Nia Thomas (Inclusive Recruitment Advisor), Adele D'Silva (Head of Workforce Supply) | An EbE representative is now included as standard in stakeholder panels for Executive Director roles. Stakeholder panels also include staff network representation, and members of the Equality, Diversity and Inclusion team. Guidance is in development, as in 9.1.